## Gantt
Task | Owner | Start Day | End Day | Duration (days) | Status | Deliverable | Visual
1.1 Config & Logos | Dev | 1 | 2 | 2 | Done | Repo, config, .env, logos, requirements | ██
1.2 Domain & AI core | Dev | 3 | 5 | 3 | Done | doc_types, models, structure, prompts, generator | ███
2.1 Backend | Dev | 6 | 8 | 3 | Done | FastAPI routes + health + validation | ███
2.2 Frontend | Dev | 9 | 12 | 4 | Done | Streamlit UI + preview/edit/export bug fix | ████
2.3 Exports | Dev | 13 | 14 | 2 | Done | DOCX/PDF/TXT + DejaVu + disclaimers | ██
3.1 Tests | Dev | 15 | 17 | 3 | Done | 63 tests, edge & fallback | ███
3.2 Screenshots | Dev | 18 | 19 | 2 | Done | 17 PNGs + captions.json | ██
3.3 Videos | Dev | 20 | 21 | 2 | Done | Demo 3–4 min + Testing 2–3 min + demo_script | ██
4.1 Phase docs | Dev | 22 | 26 | 5 | Done | 8 phases + diagrams + sheets + slides | █████
4.2 Final report & README | Dev | 27 | 28 | 2 | Done | Final_Project_Report + README + evidence + zip | ██