AI-Powered Legal Document Generator

Phase 04: Project Planning

Internship Project Submission

AI-generated template, not legal advice; have a lawyer review.

LegalEase - AI-Powered Legal Document GeneratorPhase 04 - Planning

Table of Contents

1. Planning Approach2

2. Task Schedule2

3. Gantt Chart3

4. Timeline and Weekly Deliverables3

5. Risk Register3

6. Tools and Resources4

1. Planning Approach

The project was planned as four one-week iterations that follow the six milestones of the project brief: M1 model selection and environment, M2 core generation and export, M3 API, M4 user interface, M5 deployment scripts and M6 end-to-end testing. Must-have features were scheduled first so that a working product existed by the end of week 3. Dates below are the planned schedule; the Status column shows the state of each deliverable on 25 September 2026 (Done = present in the repository and verified by running it).

2. Task Schedule

Table 1: Task list with owner, planned dates, duration (working days) and status

| ID | Task | Owner | Start | End | Days | Status |
| --- | --- | --- | --- | --- | --- | --- |
| T01 | Brainstorming and idea selection | Intern | 31 Aug | 01 Sep | 2 | Done |
| T02 | Requirement analysis (FR, NFR, user stories) | Intern | 01 Sep | 03 Sep | 3 | Done |
| T03 | M1: Model selection and dev environment | Intern | 03 Sep | 04 Sep | 2 | Done |
| T04 | System design: architecture, DFD, prompts | Intern | 07 Sep | 08 Sep | 2 | Done |
| T05 | M2: Core generation (Gemini + offline templates) | Intern | 08 Sep | 10 Sep | 3 | Done |
| T06 | M2: Export utilities (TXT, DOCX, PDF) | Intern | 10 Sep | 11 Sep | 2 | Done |
| T07 | M3: FastAPI backend (/, /health, /generate) | Intern | 14 Sep | 15 Sep | 2 | Done |
| T08 | M4: Streamlit UI (form, preview, editor, downloads) | Intern | 15 Sep | 17 Sep | 3 | Done |
| T09 | Demo mode, AI fallback and error handling | Intern | 17 Sep | 18 Sep | 2 | Done |
| T10 | M6: Automated tests (pytest) and UI checks | Intern | 21 Sep | 22 Sep | 2 | Done |
| T11 | M5: Deployment scripts (run.sh, run.bat) | Intern | 22 Sep | 22 Sep | 1 | Done |
| T12 | Screenshots, demo and testing videos | Intern | 23 Sep | 23 Sep | 1 | Done |
| T13 | Documentation, final report and presentation | Intern | 23 Sep | 25 Sep | 3 | Done |
| T14 | Mentor review of report and slides | Mentor | 25 Sep | 25 Sep | 1 | Planned |
| T15 | Final demonstration and viva | Intern + Mentor | 28 Sep | 28 Sep | 1 | Planned |

3. Gantt Chart

Figure 1: Gantt chart of the 4-week plan

Gantt_Chart.xlsx contains the same plan with a visual bar column, a day-by-day coloured grid, a native Excel stacked-bar chart, the weekly deliverables and the risk register.

4. Timeline and Weekly Deliverables

Table 2: Weekly deliverables

| Week | Focus | Deliverables |
| --- | --- | --- |
| Week 1 (31 Aug - 4 Sep) | Idea, requirements and setup | Problem statement, personas, idea comparison, FR/NFR list, user stories, Python environment and model choice. |
| Week 2 (7 - 11 Sep) | Design and core engine | Architecture, DFD, use case and flow diagrams; prompt design; ai_core generation and TXT/DOCX/PDF export. |
| Week 3 (14 - 18 Sep) | API and user interface | FastAPI routes with Pydantic validation; Streamlit form, preview, editor and downloads; Demo mode and fallback. |
| Week 4 (21 - 25 Sep) | Testing and documentation | pytest suite with coverage, UI edge-case checks, screenshots, videos, phase documents, report and slides. |

5. Risk Register

Table 3: Risk register (L = likelihood, I = impact: H/M/L)

| ID | Risk | L | I | Mitigation | Status |
| --- | --- | --- | --- | --- | --- |
| R1 | Gemini API key unavailable or free quota exhausted | H | H | Demo mode (offline templates) and automatic fallback with a clear message | Mitigated |
| R2 | Model retired or renamed (the spec used gemini-1.5-pro) | H | H | Model ID read from GEMINI_MODEL in .env; default gemini-3.8-flash | Mitigated |
| R3 | AI output inaccurate, incomplete or badly structured | M | H | Structured prompt, output validation, disclaimer, lawyer review | Mitigated |
| R4 | Prompt injection or HTML injection through user input | M | M | Inputs wrapped in <<< >>> delimiters; HTML escaped in the preview | Mitigated |
| R5 | Unicode (₹, curly quotes) breaks PDF export | M | M | fpdf2 with bundled DejaVu fonts; automated Unicode tests | Mitigated |
| R6 | Exports ignore the user's edits (bug in the spec code) | H | H | current_export_text() used for preview and all downloads; tested | Fixed |
| R7 | Backend not running during the demo | M | M | run.sh / run.bat start both servers; friendly UI error; demo checklist | Mitigated |
| R8 | Schedule slip in week 3 or 4 | M | M | Must-have features first; weekly deliverables; nice-to-have items can move | Closed |

6. Tools and Resources

Table 4: Tools and resources

| Tool | Used for |
| --- | --- |
| Python 3.13.14, VS Code, Git | Programming, editing and version control |
| FastAPI 0.141.1, Uvicorn 0.54.0, Pydantic 2.13.4 | Backend API and validation |
| Streamlit 1.64.0 | Frontend user interface |
| google-genai 2.25.0 | Google Gemini API access (model from GEMINI_MODEL) |
| python-docx 1.1.2, fpdf2 2.8.8, Pillow 12.3.0 | DOCX, PDF and image handling |
| pytest 9.0.3, pytest-cov 7.1.0, Playwright 1.63.0 | Automated tests, coverage, screenshots, UI checks and videos |
| LibreOffice, pdf2image, ffmpeg, Graphviz, matplotlib | Rendering exports, videos and diagrams |
| openpyxl 3.1.5, python-pptx 1.0.2 | Excel sheets and the presentation |

Page 1 of 1